## Deliverable 1 — Inception Report

### Full Action Plan: Weeks 1–2

Start Date: Monday, 25 May 2026 | Submission Deadline: Friday, 6 June 2026

### What the Inception Report Must Contain

The TOR specifies three formal components. Your proposal framework expands each into a set of auditable sub-outputs:

| TOR Component | What You Actually Need to Produce |
| --- | --- |
| Detailed workplan | Day-by-day schedule for the full 10-week assignment, with milestones, submission dates, and review windows |
| Methodological approach | The diagnostic-design-validation logic; data-collection instruments; document-review protocol; field-visit strategy |
| Stakeholder mapping | Named matrix of all GSD units, IOM staff, and national/international actors; roles; access levels; consultation schedule |

### Day-by-Day Action Plan

#### Day 1 — Monday, 26 May

Orientation and Access Setup

- Attend IOM Lebanon onboarding meeting with the IBG Programme Manager.

- Confirm the GSD focal point(s) — identify whether there is one empowered decision-making mechanism or multiple entry points.

- Submit your document request pack on Day 1, not later. The pack must list: all existing GSD SOPs, training manuals, session plans, presentations, previous assessment reports, and any IOM or donor-funded training materials from past projects. Every day of delay here compresses the needs assessment window.

- Request access to: the GSD Training Academy, relevant border-post contacts, and any prior IOM IBG programme documentation for Lebanon.

- Open your issue log — a simple tracker noting every access delay, document gap, or unresolved coordination question from the first day.

#### Day 2 — Tuesday, 27 May

Preliminary Desk Review — IOM and International Standards

Begin reading the core reference set. Prioritise in this order:

- IOM IBG framework documentation

- ICAO Doc 9303 (MRTDs) and ICAO Doc 9957 (Facilitation Manual, Chapter 9 — passenger data)

- OHCHR Recommended Principles and Guidelines on Human Rights at International Borders

- UNODC counter-trafficking and counter-smuggling materials

- WHO IHR Points of Entry benchmarks

- IMO maritime facilitation and digitalization standards (including March 2026 updates)

- IOM Data Protection Manual and principles

Do not attempt to master each document in full on Day 2. The objective is to extract the standards and competency benchmarks that the curriculum must align with — which you will later cross-reference against GSD's existing materials. Build a standards reference table as you read: source document, relevant standard or principle, applicable module(s).

#### Day 3 — Wednesday, 28 May

Draft Stakeholder Mapping Matrix

Produce the first working version of the stakeholder map. Structure it as a table with the following columns:

- Organisation / Unit

- Key contact (name and title where confirmed)

- Role in the consultancy (informant / reviewer / approver / end-user)

- Consultation method (interview / focus group / document review / workshop)

- Access status (confirmed / pending / to be requested)

- Scheduled consultation window

The matrix must cover all of the following actor categories:

- GSD leadership and the Training Academy

- GSD operational units: land borders, air borders (Rafic Hariri International Airport), maritime

- GSD legal and IT/data units

- IOM Lebanon IBG programme team

- Relevant national partners: LAF, Customs, Ministry of Public Health, Ministry of Interior where applicable

- International and regional actors with prior training engagement (UNHCR, UNODC, EU, INTERPOL where relevant)

#### Day 4 — Thursday, 29 May

Design the Data-Collection Instrument Set

Draft the full set of instruments you will use during the needs assessment phase. These must be ready before any field consultation begins. The minimum required set is:

- Structured Key Informant Interview (KII) guide — separate versions for: GSD leadership, academy/training staff, operational supervisors, legal/IT units, and international partners

- Focus group guide — for front-line officers and active trainers

- Site observation checklist — to be used at each border post visited

- Trainer capability assessment sheet — to assess current facilitation skills and training experience within GSD

- Training needs questionnaire — short, anonymous, for broader officer input

- Curriculum audit form — one per existing GSD training document

- Legal and standards crosswalk template — to map GSD's current legal framework against international obligations for each of the ten thematic areas

- Lessons-learned tracker — to capture inputs from prior assessments and IOM programme experience

Drafting these instruments on Day 4 means you can begin piloting them internally and with IOM counterparts on Days 5–7.

#### Day 5 — Friday, 30 May

Internal Review with IOM + Preliminary GSD Consultation

- Share the draft stakeholder map and instrument set with the IOM IBG Programme Manager for review and correction.

- Confirm the GSD consultation schedule for Week 2 — secure at least three confirmed interview slots with senior GSD interlocutors before the end of Day 5.

- Begin reading GSD materials received under the document request. Start the document review matrix for each item received. Apply the four-decision coding for each document: retain / revise / merge / retire.

- End of Week 1 self-check: document request submitted; issue log open; stakeholder map drafted; all instruments drafted; at least three Week-2 consultations confirmed.

#### Day 6 — Monday, 2 June

GSD Consultations — Leadership and Academy

Conduct the first round of Key Informant Interviews. Prioritise GSD leadership and the Training Academy in Week 2's first half, operational units in the second half. Specific objectives for these interviews:

- Understand GSD's current training governance structure and who holds decision-making authority over the Academy

- Identify which of the ten thematic areas are considered most operationally urgent by leadership

- Establish the realistic trainer pool — who can be nominated as a core trainer cohort

- Confirm which legacy materials GSD considers current and operational, versus outdated

- Identify any politically or institutionally sensitive scope boundaries early

Record all outputs in the lessons-learned tracker. Do not rely on memory or informal notes.

#### Day 7 — Tuesday, 3 June

GSD Consultations — Operational Units + Document Review

- Continue KIIs with operational supervisors: land borders, airport, maritime units.

- Run a focus group with front-line officers or trainers if logistically possible.

- Continue completing the document review matrix for all received GSD materials.

- Flag in the issue log any critical documents not yet received — apply the contingency: proceed with provisional analysis clearly marked as pending verification.

#### Day 8 — Wednesday, 4 June

GSD Consultations — Legal, IT/Data, and Partner Actors

- Conduct KIIs with GSD legal and IT/data units — these are essential for the data-protection module and for understanding any legal constraints on training content.

- Where access is confirmed, conduct a consultation with at least one international partner (UNHCR, UNODC, or equivalent) to capture lessons from prior training engagement.

- Begin drafting the preliminary field-visit plan — identify the three minimum sites to be visited during the needs assessment phase: one air-border site (Rafic Hariri International Airport), one maritime site, and at least one major land-border crossing. The field visits will occur in Weeks 3–4 under Deliverable 2, but the plan must appear in the Inception Report.

#### Day 9 — Thursday, 5 June

Inception Report Drafting — Full Day

By this point you have: the workplan logic, the methodology, the instruments, the stakeholder map, the preliminary document review findings, and the field-visit plan. Spend the full day drafting the Inception Report. The document structure should follow this sequence:

- Assignment Context and Scope — one page; operational framing of the Lebanon border environment and the consultancy purpose

- Methodological Approach — the three-phase logic; diagnostic rationale; data-collection strategy; document-review protocol; two-round field-visit design

- Stakeholder Map — the confirmed matrix

- Detailed Workplan — week-by-week Gantt or table covering all 10 weeks, with milestones, submission dates, and review windows

- Data-Collection Instrument Set — summarised with annexes attached

- Field-Visit Plan — sites, objectives, timing, and access status

- Issue Log — current open items and mitigations

- Quality Plan — how outputs will be reviewed, by whom, and at what stage

- Document Review Matrix Template — the blank tool, ready for population in Weeks 3–4

- Validation Calendar — provisional dates for the Week-9 workshop and Week-10 final submission

#### Day 10 — Friday, 6 June

Internal Review, Finalisation, and Submission

- Share the full draft with the IOM IBG Programme Manager by 09:00 for a final review.

- Incorporate any IOM corrections by midday.

- Submit the final Inception Report to IOM Lebanon by end of business — this triggers the 20% payment milestone.

- Open a revision log to track any post-submission comments received from GSD or IOM for incorporation into Deliverable 2.

### Risk Flags for Weeks 1–2

Three risks are high-probability in this environment and must be managed from Day 1:

- Document access delay: if GSD materials are not received within three working days of the Day-1 request, escalate immediately to the IOM Programme Manager. Do not wait.

- Stakeholder availability: GSD operational staff are subject to shift cycles and operational tempo. Confirm all Week-2 interview slots by end of Day 5 — not Day 8.

- Scope ambiguity: if GSD leadership and operational units give conflicting signals about training priorities in KIIs, document both positions in the issue log and flag for resolution through the IOM–GSD steering level. Do not absorb the conflict silently into the workplan.